## Sheet1
FDH Acceptance Certificate
Details
Phase: |  | Langeberg Ridge |  | Date & Time: | Nov, 24, 2024 22:53
FDA: |  | Langeberg Ridge |  | FDH: | FC1LBR1FDH1
Closest Address: |  | Langeberg Ridge |  | FDH Type: | FC1LBR1FDH1
Above Ground FDH Checklist
# | Item: | Description: |  |  | Result: | Comment
1 | Concrete | Smooth edges. No cracks or chips |  |  | Pass | Operations FiberConfig: Accepted
2 | FDH Mounting | Bolts on all 4 sides of FDH. FDH to be sturdy. |  |  | Pass | Braam Bester: pmqc comment
Below Ground FDH Checklist
# | Item: | Description: |  |  | Result: | Comment
3 | Conduit Organization | Organize each row of microducts for each route being brought into the cabinet. |  |  | Pass | Jack Sparrow: 1st comment
4 | Duct Organizers | Attached correctly and secure. Conduit to be 2" high from organizer. Staggered height. |  |  | Pass | Jack Sparrow: new comments added
Comments:
Contractor: changed to passed, PMQC: Pass after reinspection, ClientQC: Accepted
Representative Details:
| Client Representative |  | PMO Representative |  |  | Contractor Representative
| Operations FiberConfig |  | Braam Bester |  |  | Jack Sparrow
| Nov, 24, 2024 22:53 |  | Nov, 24, 2024 22:40 |  |  | Nov, 24, 2024 22:34